## Sheet1
WBS | Task Name | Duration | Resource Names | Cost | Work
| Gantt Chart | 190 days |  | 1329092 | 3,405.6 hrs
1 | Application Rationalization | 18 days |  | 60900 | 172.8 hrs
1.1 | Analyze architecture | 7 days |  | 2520 | 40.8 hrs
1.1.2 | Eliminate redundant applications | 1 day | Analyst[50%],R&D Engineers[50%] | 440 | 8 hrs
1.1.1 | Analyze application portfolio | 3 days | Business Analyst 1[20%] | 240 | 4.8 hrs
1.1.3 | Renovate worthwhile applications | 1 day | Developer[50%],Developer 2[50%],Developer 3[50%],Developer 4[50%],Cloud Developer - 1[50%],DevOps Engineer[50%],Web Developer -1[50%] | 1840 | 28 hrs
1.2 | Analyze security standards | 8 days |  | 58380 | 132 hrs
1.2.2 | Business Continuity planning | 1 day | Project Manager | 720 | 8 hrs
1.2.3 | Information Security policy | 2 days | Security Analyst[50%],Business Analyst 1[50%],System Architect[50%],Technology Analyst[50%],Solution Architect[50%] | 2440 | 40 hrs
1.2.1 | Decide cloud architecture - public/private/hybrid architecture | 3 days | System Architect[50%],Cloud Storage Admin-1[50%],Data Center Admin - 1[50%],Infrastructure Engineer[50%],Network Administrator[50%],System Software[1],Technology Analyst[50%],Solution Architect[50%] | 55220 | 84 hrs
2 | Vendor Selection | 7 days |  | 4360 | 60 hrs
2.1 | Selection criteria | 3 days |  | 2280 | 36 hrs
2.1.2 | Defining features criteria | 1 day | Business Analyst 1[50%],Technology Analyst[50%] | 380 | 8 hrs
2.1.1 | Defining cost criteria | 1 day | Financial Analyst[50%],Business Analyst 1[50%],Cloud Aggies Consulting Firm(Likita) [50%],Project Manager 2[50%] | 1120 | 16 hrs
2.1.3 | Defining support Criteria | 1 day | System Architect[50%],Technology Analyst[50%],Solution Architect[50%] | 780 | 12 hrs
2.2 | Vendor scorecard | 4 days |  | 2080 | 24 hrs
2.2.1 | Evaluate vendors | 1 day | Business Analyst 1[50%],Cloud Aggies Consulting Firm(Aarthi) [50%],Cloud Aggies Consulting Firm(Atif) [50%],Cloud Aggies Consulting Firm(Likita) [50%],Cloud Aggies Consulting Firm(Saddam) [50%] | 1800 | 20 hrs
2.2.2 | Select Vendor | 1 day | Business Analyst 3[30%],Cloud Aggies Consulting Firm(Saddam) [20%] | 280 | 4 hrs
3 | Feasibility and impact analysis | 14 days |  | 10800 | 128 hrs
3.2 | Probability impact analysis | 4 days | Business Analyst 1[50%],Cloud Aggies Consulting Firm(Aarthi) [50%],Cloud Aggies Consulting Firm(Atif) [50%],Cloud Aggies Consulting Firm(Likita) [50%],Cloud Aggies Consulting Firm(Saddam) [50%] | 7200 | 80 hrs
3.1 | Feasibility report | 6 days | Business Analyst 3[50%],Cloud Aggies Consulting Firm(Atif) [50%] | 3600 | 48 hrs
4 | Initial Setup | 51 days |  | 697296 | 740.8 hrs
4.1 | Determine scope of implementation | 8 days |  | 9860 | 144 hrs
4.1.2 | Determine requirements and goals | 5 days | Business Analyst 2[50%],Project Manager 2[50%],Technology Analyst[50%] | 3300 | 60 hrs
4.1.1 | Document scope of Cloud implementation | 5 days | Business Analyst 3[50%],Cloud Storage Admin-1[50%],Cloud Aggies Consulting Firm(Atif) [50%] | 4400 | 60 hrs
4.1.3 | Introduction meeting implementation team. | 3 days | Project Manager | 2160 | 24 hrs
4.2 | Coordination and quality management | 15 days |  | 5536 | 92.8 hrs
4.2.2 | Determine the level of high availability required | 6 days | Project Manager 2[50%],Data Center Admin - 1[50%] | 3360 | 48 hrs
4.2.1 | Quality management on throughout all phases | 8 days | Quality Analyst[50%],Technology Analyst[20%] | 2176 | 44.8 hrs
4.3 | Technical intake and Fuctional Intake | 15 days |  | 164260 | 192 hrs
4.3.2 | Infrastructure requirements for cloud setup | 5 days | Business Analyst 2[50%],Cloud Storage Admin-1[50%],Network Equipments[1],Application Servers[1],System Software[1] | 152400 | 40 hrs
4.3.1 | Technical and Functional intake meeting | 4 days | Business Analyst 3[50%],Developer 3[50%],Developer 4[50%],Project Manager 2[50%],Technology Analyst[50%],Hotel Accomodation[1],Plane Ticket[1],Data Center Admin - 1[50%],Cloud Developer - 1[50%],Web Developer -1[50%],DevOps Engineer[50%] | 11340 | 144 hrs
4.3.3 | User/Roles/Groups/Rules model | 1 day | Security Analyst[50%],Data Center Admin - 1[50%] | 520 | 8 hrs
4.4 | Deliver implementation plan | 8 days |  | 4160 | 68 hrs
4.4.1 | Document requirements and goals. | 2 days | Business Analyst 2 | 800 | 16 hrs
4.4.4 | Update estimate planning based on implementation plan. | 2 days | Business Analyst 2[50%],Project Manager 2[50%] | 960 | 16 hrs
4.4.2 | Document required functional and technical configuration | 3 days | Business Analyst 3[50%] | 600 | 12 hrs
4.4.3 | Build architecture Diagram. | 3 days | System Architect[50%],Solution Architect[50%] | 1800 | 24 hrs
4.5 | Infrastructure Setup | 11 days |  | 302000 | 44 hrs
4.5.2 | Operating system installation | 4 days | Developer 4[50%],System Software[1] | 50640 | 16 hrs
4.5.1 | Install hardware systems | 4 days | Infrastructure Engineer[50%],Network Equipments[1],Application Servers[1],System Software[1] | 150640 | 16 hrs
4.5.3 | Network configuration of hardware systems | 3 days | Network Administrator[50%],Network Equipments[1],Application Servers[1] | 100720 | 12 hrs
4.6 | Setting up Cloud configuration for high availability | 16 days |  | 156920 | 124 hrs
4.6.3 | Setup backups | 3 days | Infrastructure Engineer[50%],Support Analyst[50%],Data Server[1],Backup Data Server[1],Data Center Admin - 1[50%] | 101920 | 36 hrs
4.6.1 | Configure Repository For High Availability | 5 days | Network Administrator[50%],Data Server[1],Data Center Admin - 1[50%] | 52600 | 40 hrs
4.6.2 | Test failover strategy | 6 days | Quality Analyst[50%],Data Analyst[50%] | 2400 | 48 hrs
4.7 | Cloud Control Functional configuration | 13 days |  | 54560 | 76 hrs
4.7.1 | Setup Cloud and user roles | 4 days | Cloud Storage Admin-1[50%],Security Analyst[50%],Cloud Storage Admin -2[50%] | 3200 | 48 hrs
4.7.2 | Setup S/W Library for cloud functionality | 4 days | Developer 2[50%],System Software[1] | 50640 | 16 hrs
4.7.3 | Add Host targets which are going to be used for Cloud | 3 days | Security Analyst[50%] | 720 | 12 hrs
5 | Data Migration | 33 days |  | 128480 | 480 hrs
5.3 | Migration Strategy | 6 days | Business Analyst 3[50%],System Architect[50%],Solution Architect[50%] | 4800 | 72 hrs
5.1 | Assessment | 10 days | Cloud Storage Admin-1[50%],Data Analyst,Cloud Storage Admin -2[50%] | 9600 | 160 hrs
5.4 | Migration | 6 days | Cloud Storage Admin-1[50%],Data Analyst,Developer,System Architect[50%],Data Server[1],Cloud Storage Admin -2[50%],Solution Architect[50%] | 61280 | 192 hrs
5.2 | Pilot | 7 days | Data Analyst,Data Server[1] | 52800 | 56 hrs
6 | Application Migration | 41 days |  | 305400 | 828 hrs
6.1 | Initiation | 11 days | Business Analyst 2,Cloud Storage Admin-1[50%],System Architect[50%],Application Servers[1],Cloud Storage Admin -2[50%],Solution Architect[50%] | 67160 | 264 hrs
6.2 | Deploy cloud environment | 7 days | Developer 2[50%],System Architect,Application Servers[1],Developer 3[50%],Developer 4[50%],Cloud Developer - 1[50%],Web Developer -1[50%],DevOps Engineer[50%],Solution Architect[50%] | 67640 | 252 hrs
6.3 | Install and configure applications | 7 days | Developer 2[50%],Technology Analyst[50%],Application Servers[1],System Software[1],Developer 3[50%],Developer 4[50%],Cloud Developer - 1[50%],DevOps Engineer[50%],Web Developer -1[50%],Solution Architect[50%] | 115540 | 224 hrs
6.4 | Production cloud migration | 11 days | Project Manager 2[50%],Technology Analyst[50%],Application Servers[1] | 55060 | 88 hrs
7 | Data Network Optimization | 16 days |  | 54800 | 76 hrs
7.1 | Analyze network usage | 6 days | Network Administrator[50%],Data Center Admin - 1[50%] | 3120 | 48 hrs
7.2 | Optimize bandwidth and ensure high availability | 7 days | Network Administrator[50%],Network Equipments[1] | 51680 | 28 hrs
8 | Change management and consolidation | 30 days |  | 46416 | 696 hrs
8.1 | Post implementation tasks and support | 18 days |  | 11040 | 184 hrs
8.1.2 | Periodic Cloud infrastructure usage analysis | 9 days | Cloud Storage Admin-1[50%],Support Analyst,Cloud Storage Admin -2[50%] | 8640 | 144 hrs
8.1.1 | Periodic health checks of cloud infrastructure | 5 days | Support Analyst[50%],Support Manager[50%] | 2400 | 40 hrs
8.2 | Training and Review | 24 days |  | 21936 | 256 hrs
8.2.3 | Expansion planning with stakeholders | 8 days | Cloud Aggies Consulting Firm(Aarthi) [20%],Cloud Aggies Consulting Firm(Atif) [20%],Cloud Aggies Consulting Firm(Likita) [20%],Cloud Aggies Consulting Firm(Saddam) [20%],Project Manager 2[20%] | 6016 | 64 hrs
8.2.2 | Reviews of Cloud and Management infrastructure | 7 days | Cloud Storage Admin-1[50%],Cloud Aggies Consulting Firm(Saddam) ,Cloud Storage Admin -2[50%] | 9520 | 112 hrs
8.2.1 | Workshop for Administrators and end users | 5 days | Trainer[50%],Hotel Accomodation[1],Plane Ticket[1],Subject Matter Expert[50%],Administration Trainer[50%],Data Center Admin - 1[50%] | 6400 | 80 hrs
8.3 | Operations and Maintenance | 10 days |  | 13440 | 256 hrs
8.3.1 | Includes cloud patches for bugs from initial review | 8 days | Developer 2,Quality Analyst,Support Analyst[50%],Support Manager[50%] | 9600 | 192 hrs
8.3.2 | Operational Support | 8 days | Support Analyst[50%],Support Manager[50%] | 3840 | 64 hrs
9 | Project Closure | 14 days |  | 20640 | 224 hrs
9.1 | Close Project | 6 days | Cloud Aggies Consulting Firm(Atif) ,Cloud Aggies Consulting Firm(Likita) ,Cloud Aggies Consulting Firm(Saddam) ,Project Manager 2 | 17760 | 192 hrs
9.2 | Archive lessons learned | 4 days | Project Manager | 2880 | 32 hrs

## Sheet2
Resource Name | Type | Initials | Max. Units | Std. Rate | fixed cost | Base Calendar
Trainer | Work | T | 100% | $35.00/hr |  | Standard
Developer | Work | D | 100% | $40.00/hr |  | Standard
Developer 2 | Work | D | 100% | $40.00/hr |  | Standard
Developer 3 | Work |  | 100% | $40.00/hr |  | Standard
Developer 4 | Work |  | 100% | $40.00/hr |  | Standard
Infrastructure Engineer | Work |  | 100% | $40.00/hr |  | Standard
Technology Analyst | Work | T | 100% | $45.00/hr |  | Standard
Analyst | Work | A | 100% | $50.00/hr |  | Standard
Business Analyst 1 | Work | B | 100% | $50.00/hr |  | Standard
Data Analyst | Work | D | 100% | $50.00/hr |  | Standard
Quality Analyst | Work | Q | 100% | $50.00/hr |  | Standard
Business Analyst 2 | Work | B | 100% | $50.00/hr |  | Standard
Business Analyst 3 | Work | B | 100% | $50.00/hr |  | Standard
Support Analyst | Work | S | 100% | $50.00/hr |  | Standard
R&D Engineers | Work | R | 100% | $60.00/hr |  | Standard
Security Analyst | Work | S | 100% | $60.00/hr |  | Standard
System Architect | Work | S | 100% | $60.00/hr |  | Standard
Financial Analyst | Work | F | 100% | $60.00/hr |  | Standard
Network Administrator | Work |  | 100% | $60.00/hr |  | Standard
Cloud Storage Admin-1 | Work | C | 100% | $70.00/hr |  | Standard
Project Manager 2 | Work | P | 100% | $70.00/hr |  | Standard
Cloud Storage Admin -2 | Work | C | 100% | $70.00/hr |  | Standard
Data Center Admin - 1 | Work | D | 100% | $70.00/hr |  | Standard
Subject Matter Expert | Work | S | 100% | $70.00/hr |  | Standard
Administration Trainer | Work | A | 100% | $70.00/hr |  | Standard
Support Manager | Work | S | 100% | $70.00/hr |  | Standard
Project Manager | Work | P | 100% | $90.00/hr |  | Standard
Solution Architect | Work | S | 100% | $90.00/hr |  | Standard
Cloud Aggies Consulting Firm(Atif) | Work | C | 100% | $100.00/hr |  | Standard
Cloud Aggies Consulting Firm(Saddam) | Work | C | 100% | $100.00/hr |  | Standard
Cloud Aggies Consulting Firm(Likita) | Work | C | 100% | $100.00/hr |  | Standard
Cloud Aggies Consulting Firm(Aarthi) | Work | C | 100% | $100.00/hr |  | Standard
Cloud Developer - 1 | Work | C | 100% | $100.00/hr |  | Standard
Web Developer -1 | Work | W | 100% | $100.00/hr |  | Standard
DevOps Engineer | Work | D | 100% | $100.00/hr |  | Standard
Hotel Accomodation | Material |  |  |  | 55000
Plane Ticket | Material |  |  |  | 55300
Network Equipments | Material |  |  |  | 200000
Application Servers | Material |  |  |  | 200000
System Software | Material |  |  |  | 200000
Data Server | Material |  |  |  | 200000
Backup Data Server | Material |  |  |  | 200000