## Application Rationalization
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Application Rationalization
Sub Tasks
Analyze Architecture | I | A | R | R | R | C | C | C | C | C | C | C | C | C | I | R | I |  | R | R |  |  | I |  | R | R
Analyze security standards | I | A | I | I | I | C | C | C | C | [5 empty] | I | C | I |  | R | R |  |  | R |  | R

## Vendor Selection
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Vendor Selection
Sub Tasks
Selection Criteria | I | A |  |  |  | C | C | C | [6 empty] | C | C | C |  | R | R | [5 empty] | C
Vendor Scorecard | [18 empty] | R | R

## Feasibility and Impact Analysis
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Feasbility and Impact Analysis
Sub Tasks
Probability Impact Analysis | I | I | C | C | C | C | C | C | C | [6 empty] | C | C |  | R | R |  |  | C |  | C | C
Feasibility Report | I | I |  |  |  | C | C | C | C | [9 empty] | R | R | [5 empty] | C

## Initial Setup
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Initial Setup
Sub Tasks
Dtermine Scope of Implementation | I | A | C | C | C | C | C | C | C |  | C | C | C | C | A |  |  |  | R | R | [5 empty] | C
Coordination and Quality Management | [18 empty] | R | R
Technical Intake and Functional intake | I | A | [15 empty] | C | R | R | [5 empty] | C
Deliver implementation plan | [18 empty] | R | R
Infrastructure setup |  | A | [13 empty] | R |  |  | R | R
Set up cloud configuration | I | A | C | C | C | [5 empty] | C | C | C | C |  |  |  |  | R | R
Cloud control fucntional configuration |  |  | C | C | C | [13 empty] | R | R

## Data Migration
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Data Migration
Sub Tasks
Migration Strategy |  | I | R | R | R | C | C | C | C | [6 empty] | C | C |  | C | C |  |  |  |  | C
Assessment |  |  | C | C | C | C | C | C | C | [9 empty] | R | R
Migration |  | A | C | C | C | C | C | C | C | C | C | C | C | C |  |  |  |  | R | R | C |  |  |  | C
Pilot |  | A | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C |  | R | R | C |  |  |  | C | C

## Application Migration
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Application Migration
Sub Tasks
Initiation |  |  | C | C | C | C | C | C | C | [6 empty] | C |  |  | R | R | C |  |  |  | C | C
Deploy cloud environment |  | A | C | C | C | C | C | C | C | [6 empty] | C |  |  | R | R | C |  | C |  | C | C
Install and configure applications | [10 empty] | C | C | C | C |  | C |  |  | R | R
Production cloud migration |  |  | C | C | C | C | C | C | C | [9 empty] | R | R | C

## Data Network Optimization
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Data Network Optimization
Sub Tasks
Analyze network usage |  |  | C | C | C | C | C | C | C | [6 empty] | C | C |  | R | R | C | C | C | C | C | C
Optimize bandwidth and ensure high availability | [5 empty] | C | C | C | C |  | C | C | C | C |  | C | C |  | R | R | C | C |  |  |  | C

## Change Management and Consolida
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Change Management and Consolidation
Sub Tasks
Post implementation tasks and support | [5 empty] | C | C | C | C | [9 empty] | R | R | C | C |  | C
Training and review |  |  | C | C | C | C | C | C | C | [9 empty] | R | R | [6 empty] | C
Operation and Maintenance | [17 empty] | C | R | R |  | C |  | C

## Project Closure
Resource Responsibility R - Primary Responsibility A - Approval Authority C - Consulting (Contributor or Reviewer) I - Information Only (Select from drop down list) | C Suite | CTO | Business Analyst 1 | Business Analyst 2 | Business Analyst 3 | Cloud Aggies Consulting - Aarthi | Cloud Aggies Consulting - Atif | Cloud Aggies Consulting - Likita | Cloud Aggies Consulting - Saddam | Data Analyst | Developer 1 | Developer 2 | Developer 3 | Developer 4 | Financial Analyst | Infrastructure Engineer | Network Administrator | Operations Manager | Project Manager 1 | Project Manager 2 | Quality Analyst | R&D Engineer | Security Analyst | Support Analyst | System Architect | Technology Analyst | Trainer
TASK - Project Closure
Sub Tasks
Archive lessons learned |  |  | C | C | C | [13 empty] | R | R | [6 empty] | C
Close project | A | A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | R | R | I | I | I | I | I | I | I

## Responsibility
R
A
C
I